## Naming
[N] = New
[R] = Replacement
R = Rockhampton-Gce-Caves --- if Caves or Gracemere there will generally be a reference to them in the name
C = Coast
M = Mt Morgan
Marl = Marlborough
O = Ogmore

## Water (New Works)
NEW Capital Works Program
[7 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[6 empty] | Yr | 2011/2012 | 2012/2013 | 2013/2014 | 2014/2015 | 2015/2016 | 2016/2017 | 2017/2018 | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | 2022/2023 | 2023/2024 | 2024/2025 | 2025/2026 | 2026/2027 | 2027/2028 | 2028/2029 | 2029/2030 | 2030/2031 | 2031/2032
| Project Category/Catchment | Proj. description | Est. Cost | Prop. Const.Date | Funding | Subsidy Available
|  |  | ($) |  |  | (%)
0959166 | R - W Barrage Install Survey control points | Water | 58400 | 2011 | L |  | 0 2011/2012: 58400
'0583053 | R - Water System leakage & pressure management | Water | 200000 | 2011 | L |  | 0 2011/2012: 200000
'0943017 | C - Misc RTK Equipments (1 Base Stn + 7 Rovers + 1 Repeater) | Water | 48000 | 2011 | RES |  | 0 2011/2012: 48000
'0959033 | M - W No7 Dam Installation of Safety Buoys | Water | 77900 | 2011 | L |  | 0 2011/2012: 77900
'0959034 | C - W Main (Trunk) Emu Park West Reservoir | Water | 800000 | 2011 | CW |  | 0 2011/2012: 800000
'0959035 | R - WPS Ramsay Creek Augmentation & Yaamba Rd PRV's | Water | 58000 | 2011 | L |  | 0 2011/2012: 58000
'0959038 | R - W GWTP Control Room Equipment | Water | 87600 | 2011 | L |  | 0 2011/2012: 87600
0986578 | [N] - Marl WTP Capacity Upgrade | Water | 30000 | 2011 | L |  | 0 2011/2012: 30000
0959191 | ML - WPS Marlborough Installation - (RO Plant site) | Water | 9070 | 2011 | DEPN |  | 0 2011/2012: 9070
0954172 | Marl - W Marlborough Drinking Water Service (RO Plant) | Water | 185620 | 2011 | L |  | 0 2011/2012: 185620
0966566 | ML WPS Electrical Upgrade | Water | 48660 | 2011 | DEPN25000L23660 |  | 0 2011/2012: 48660
0966567 | ML WTP Backup Generator installation | Water | 3760 | 2011 | L |  | 0 2011/2012: 3760
0954357 | O - Water Reticulation - Install Ball Va | Water | 13650 | 2011 | DEPN |  | 0 2011/2012: 13650
0976593 | R - W Reservoir Kabra (Gce) Potable Water supply site procurement | Water | 5000 | 2011 | L |  | 0 2011/2012: 5000
0581048 | R - WPS Norman Rd Upgrade pumps (8028) | Water | 11700 | 2011 | L |  | 0 2011/2012: 11700
0943003 | R-W GWTP Highlift switchboard upgrade / | Water | 173000 | 2011 | L |  | 0 2011/2012: 173000
0974053 | R - GWTP New Experion Servers and Associ | Water | 14000 | 2011 | L |  | 0 2011/2012: 14000
0943004 | R-W GWTP Travelling bridges switchboard | Water | 140000 | 2011 | L |  | 0 2011/2012: 140000
0583077 | GWTP backup generator | Water | 510000 | 2011 | L |  | 0 2011/2012: 510000
0580989 | R - WPS Highligt Pump 5 transformer cabl | Water | 27120 | 2011 | L |  | 0 2011/2012: 27120
0687945 | M - Water Dam No7 Installation & survey | Water | 18750 | 2011 | L |  | 0 2011/2012: 18750
0986575 | [N] C - WPS Booster Cliff St pressure im | Water | 20000 | 2011 | L |  | 0 2011/2012: 20000
0882801 | M - WTP Chlorination and Instrumentation | Water | 105100 | 2011 | L |  | 0 2011/2012: 105100
0580981 | C - Water Reservoir St Faiths No 3 Const | Water | 320000 | 2011 | CW210688L109312 |  | 0 2011/2012: 320000
0973964 | C - W Main 150mm James Street (Arthur - | Water | 89710 | 2011 | L |  | 0 2011/2012: 89710
0986574 | [N] C - W Main 100mm Cliff St pressure i | Water | 55000 | 2011 | L |  | 0 2011/2012: 55000
0581028 | C - Water Main 375mm Hill St Emu Park Au | Water | 9730 | 2011 | L |  | 0 2011/2012: 9730
0799899 | C - WTP Woodbury Install new compressor | Water | 11700 | 2011 | RES |  | 0 2011/2012: 11700
0583057 | C - Magflo at Waterpark Ck Highlift WPS | Water | 54000 | 2011 | RES31000L23000 |  | 0 2011/2012: 54000
0640897 | C-W-Reservoir Kinka West | Water | 5025 | 2011 | RES |  | 0 2011/2012: 5025
0943016 | C-W Keppel Sands WPS Booster and pipework | Water | 17500 | 2011 | CW |  | 0 2011/2012: 17500
0943013 | 0943013 - Trunk Water Main Easements | Water | 57236 | 2011 | L |  | 0 2011/2012: 57236
0943022 | Rockhampton - Albert St SLMP 150 main In | Water | 73500 | 2011 | L |  | 0 2011/2012: 73500
'0581042 | R-W-Barrage Cathodic Protection | Water | 150000 | 2011 | L |  | 0 2011/2012: 150000
0581056 | R - Water TPGlenmore Lagoons Expansion D | Water | 1109700 | 2011 | L609700D500000 |  | 0 2011/2012: 1109700
0986573 | [N] Water Quality Options Report | Water | 100000 | 2011 | L |  | 0 2011/2012: 100000
581085 | [N] R - Water Barrage Crane Restore | Water | 1209052 | 2012 |  |  | 1 2012/2013: 1209052
959005 | [R] C - WTP Yeppoon PLC & Comms | Water | 351724 | 2012 |  |  | 1 2012/2013: 351724
987952 | [R] R Glenmore Lowlift WPS Switchboard Upgrade | Water | 274785 | 2012 |  |  | 1 2012/2013: 274785
987954 | [R] C Waterpark Ck Lowlift screen renewal | Water | 10991 | 2012 |  |  | 1 2012/2013: 10991
943005 | [R] R-WPS and Reservoir Caves | Water | 63793 | 2012 |  |  | 1 2012/2013: 63793
583053 | [N] Water System leakage & pressure management | Water | 516045 | 2012 | L |  | 1 2012/2013: 516045
943022 | [N] Rockhampton - Albert St SLMP 150 main Interconnections | Water | 131897 | 2012 |  |  | 1 2012/2013: 131897
959034 | [N] C - W Main (Trunk) Emu Park West Reservoir | Water | 3158797 | 2012 | CW |  | 1 2012/2013: 3158797
959039 | [N] C - W Reservoir St Faiths Rechlorination | Water | 54957 | 2012 |  |  | 1 2012/2013: 54957
959040 | [N] R - W Main Crossing QR Reserve Anniki St | Water | 21983 | 2012 |  |  | 1 2012/2013: 21983
984862 | [N] C - W Main 375mm Tanby Heights Stage 1A to 1D (Committed Expenditure through Infrastructure Agreement) | Water | 588542 | 2012 | L |  | 1 2012/2013: 588542
987953 | [N] R GWTP No. 2 Sedimentation Tank 2 Instrumentation | Water | 10992 | 2012 |  |  | 1 2012/2013: 10992
987955 | [N] M No7 Dam WPS upgrade | Water | 49460 | 2012 |  |  | 1 2012/2013: 49460
984822 | [N] R - W Gce Industrial 300mm trunk water main | Water | 0 | 2012 | L |  | 1 2012/2013: 0
989137 | [N] R - W Lucas Street Pump Station Upgrade | Water | 0 | 2012 |  |  | 1 2012/2013: 0
| [N] - R GIA Stg 1 - W Main (Trunk) 200mm Somerset Rd east of Stewart St | Water | 300000 | 2012 |  |  | 1 2012/2013: 300000
| [N] - R GIA Stg 1 - W Main (Trunk) 300mm Somerset Rd west of Stewart St | Water | 500000 | 2012 |  |  | 1 2012/2013: 500000
0984824 | R - WPS Agnes St Upgrade (outlet pipework) to Gracemere supply | Water | 200000 | 2012 | CW/L |  | 1 2012/2013: 200000
581042 | [N] R - Water Barrage Cathodic Protection Installation | Water | 549569 | 2013 |  |  | 2 2013/2014: 549569
945553 | [N] R - W Bulk Water Offtakes | Water | 179659 | 2013 |  |  | 2 2013/2014: 179659
943017 | [N] C- Permanent RTK Base Station and Repeater Installations | Water | 87931 | 2013 | L |  | 2 2013/2014: 87931
987951 | [N] GWTP 4 x Endress & Hauser turbidity meters | Water | 329741 | 2013 |  |  | 2 2013/2014: 329741
984880 | [N] C-W-Reservoir West Emu Park | Water | 2747845 | 2013 | CW/L |  | 2 2013/2014: 2747845
959034 | [N] C - W Main (Trunk) Emu Park West Reservoir | Water | 769396 | 2013 |  |  | 2 2013/2014: 769396
583053 | [N] Water System leakage & pressure management | Water | 516045 | 2013 |  |  | 2 2013/2014: 516045
984822 | [N] R - W Gce Industrial 300mm trunk water main | Water | 0 | 2013 |  |  | 2 2013/2014: 0
| [N] - R GIA Stg 2 - W Main (Trunk) 300mm Douglas St between MacQuarie and Stewart St | Water | 550000 | 2013 |  |  | 2 2013/2014: 550000
| [N] - R GIA Stg 2 - W Main (Trunk) 300mm Stewart St between Douglas St & Somerset Rd | Water | 330000 | 2013 |  |  | 2 2013/2014: 330000
| [N] - R W Main (Trunk) 300mm Athelstane to Gracemere duplication | Water | 1000000 | 2013 |  |  | 2 2013/2014: 1000000
984814 | [N] R-W-Rockhampton – Rosewood Dr 150 Water Main Duplication | Water | 65948 | 2014 |  |  | 3 2014/2015: 65948
581042 | [N] R - Water Barrage Cathodic Protection Installation | Water | 1099138 | 2014 | CW/L | #VALUE! | 3 2014/2015: 1099138
| [N] - R W Main (Trunk) 300mm Athelstane to Gracemere duplication | Water | 1000000 | 2014 | CW/L | #VALUE! | 3 2014/2015: 1000000
987949 | [N] R - W Gracemere Mawdesley Hill Pump Station Upgrade | Water | 200000 | 2015 | CW/L | 235776.6927 | 4 2015/2016: 200000
984888 | R - GIA Stg 6 - W Main 300mm extension to Kabra Reservoir site | Water | 0 | 2015 | CW/L | 0 | 4 2015/2016: 0
984888 | R - GIA Stg 6 - W Main 300mm extension to Kabra Reservoir site | Water | 0 | 2015 | CW/L | 0 | 4 2015/2016: 0
| C-W-Main Woodwind Valley Trunk Distribution | Water | 625000 | 2015 | CW/L | 736802.1648 | 4 2015/2016: 625000
| C-W-Main (Trunk) 375mm Tanby Rd heading south from Taranganba Rd | Water | 1100000 | 2015 | CW/L | 1296771.8101 | 4 2015/2016: 1100000
| C - W Main (Trunk) 200mm Kinka West HZ | Water | 245000 | 2015 | CW/L | 288826.4486 | 4 2015/2016: 245000
| R - W Main (Trunk) Douglas St (Gce) | Water | 495798 | 2015 | CW/L | #VALUE! | 4 2015/2016: 495798
| C - W Main (Trunk) 375mm Mulambin Res Inlet | Water | 53500 | 2015 |  |  | 4 2015/2016: 53500
| C - W Main (Trunk) 375mm Mulambin Res Outlet | Water | 53500 | 2015 | CW/L | #VALUE! | 4 2015/2016: 53500
989137 | [N] R - GIA Stg 3 - WPS Lucas St (Gce) | Water | 435000 | 2015 | CW/L | #VALUE! | 4 2015/2016: 435000
| [N] - R GIA Stg 3 - 300mm W Main (Trunk) MacQuarie St between Lucas St & Douglas St | Water | 1000000 | 2015 | CW/L | #VALUE! | 4 2015/2016: 1000000
| [N] - R W Main (Trunk) 300mm Athelstane to Gracemere duplication | Water | 1500000 | 2015 | CW/L | #VALUE! | 4 2015/2016: 1500000
| C - W Main (Trunk) 375mm Svendsen Rd | Water | 1400000 | 2016 | CW/L | #VALUE! | 5 2016/2017: 1400000
| C-W-Reservoir West Emu Park | Water | 865000 | 2017 | CW/L | #VALUE! | 6 2017/2018: 865000
| [N] - R GIA Stg 4 - W Main (Trunk) 200mm & 300mm Ring main extensions | Water | 900000 | 2017 | CW/L | #VALUE! | 6 2017/2018: 900000
987948 | [N] R - W Gracemere ground level 5ML Lucas St Reservoir duplication | Water | 549569 | 2019 | CW/L | #VALUE! | 8 2019/2020: 549569
| [N] - R GIA Stg 5 - W Main (Trunk) 200mm & 300mm Ring main completion | Water | 1000000 | 2019 | CW/L | #VALUE! | 8 2019/2020: 1000000
987948 | [N] R - W Gracemere ground level 5ML Lucas St Reservoir duplication | Water | 2500000 | 2020 | CW/L | 3620341.0056 | 9 2020/2021: 2500000
| M - W Main (Trunk) 200mm Black St | Water | 0 | 2020 | CW/L | 0 | 9 2020/2021: 0
| C - WPS Hawke St | Water | 201000 | 2020 | CW/L | 291075.4169 | 9 2020/2021: 201000
| C - W Main (Trunk) 200mm Hewitt St HZ | Water | 520000 | 2020 | CW/L | 753030.9292 | 9 2020/2021: 520000
| C - W Reservoir Mulambin 4ML | Water | 865000 | 2020 | CW/L | 1252637.988 | 9 2020/2021: 865000
| R - W Main (Trunk) 500mm Edenbrook East | Water | 1600000 | 2020 | CW/L | 2317018.2436 | 9 2020/2021: 1600000
| R - W Gce Industrial 200mm Distrib Main | Water | 0 | 2020 | CW/L | 0 | 9 2020/2021: 0
984888 | [N] R - GIA Stg 6 - W Main 300mm extension to Kabra Reservoir site | Water | 800000 | 2020 | CW/L | 1158509.1218 | 9 2020/2021: 800000
| C - W Main (Trunk) 375mm Kinka West Res Inlet | Water | 267000 | 2020 | L | #VALUE! | 9 2020/2021: 267000
| C - W Main (Trunk) 375mm Kinka West Res Outlet | Water | 54000 | 2020 | L | #VALUE! | 9 2020/2021: 54000
| C - W Main (Trunk) 200mm West Emu Park HZ heading East | Water | 520000 | 2020 | CW/L | #VALUE! | 9 2020/2021: 520000
| C - W Main (Trunk) 200mm West Emu Park HZ heading West | Water | 520000 | 2020 | CW/L | #VALUE! | 9 2020/2021: 520000
| C - W Reservoir Great Barrier Reef Resort 4ML | Water | 865000 | 2020 | CW/L | #VALUE! | 9 2020/2021: 865000
| C - WPS Svendsen Rd | Water | 220000 | 2020 | CW/L | #VALUE! | 9 2020/2021: 220000
| C - WPS West Emu Park HZ | Water | 220000 | 2020 | CW/L | #VALUE! | 9 2020/2021: 220000
976593 | R - W Reservoir Kabra (Gce) 10ML | Water | 2155000 | 2020 | CW/L | #VALUE! | 9 2020/2021: 2155000
| C - WPS Kinka West HZ | Water | 220000 | 2020 | L | #VALUE! | 9 2020/2021: 220000
| C - W Main (Trunk) 375mm Hartley St to Zilzie LZ | Water | 855000 | 2020 |  |  | 9 2020/2021: 855000
| R-W-Main (Trunk) 200mm Lawrie St Gracemere | Water | 29000 | 2023 |  |  | 12 2023/2024: 29000
| R-W-Main (Trunk) 500mm Lawrie St Gracemere | Water | 405000 | 2023 |  |  | 12 2023/2024: 405000
| C-W Main (Trunk) 200mm Adelaide Park HZ | Water | 347000 | 2025 |  |  | 14 2025/2026: 347000
| C-W-Reservoir Kinka West 4ML | Water | 865000 | 2025 |  |  | 14 2025/2026: 865000
| C-W Main (Trunk) 375mm Carige Blvd | Water | 3741000 | 2025 |  |  | 14 2025/2026: 3741000
| C - WPS Inverness HZ | Water | 220000 | 2025 |  |  | 14 2025/2026: 220000
| C - WPS Keppel Sands Booster | Water | 220000 | 2025 |  |  | 14 2025/2026: 220000
| R - W Main (Trunk) 300mm Stanwell Industrial (Gce) | Water | 1500000 | 2025 |  |  | 14 2025/2026: 1500000
| C-W-Reservoir Tanby Range 4ML | Water | 865000 | 2030 |  |  | 19 2030/2031: 865000
| C-WPS Woodwind Valley Booster | Water | 150000 | 2032
| Total Proposed Cap X |  | 52513088 |  |  |  | 4698431 | 7443018 | 7060186 | 2165086 | 5707798 | 1400000 | 1765000 | 0 | 1549569 | 12382000 | 0 | 0 | 434000 | 0 | 6893000 | 0 | 0 | 0 | 0 | 865000 | 0
[7 empty] | 14787732.57 | 15664799 | 15616575 | 10954894 | 12028209 | 7496243 | 7472189 | 5680622 | 3742586.33 | 15518740.41 | 1439000 | 1519925 | 1684329 | 1553512 | 8504451 | 1337985 | 1247044 | 1200479 | 170084 | 1508446 | 99107
| Projects submitted but not approved in 2012-13 as at 08-05-12 | [5 empty] | 2 2013/2014: 42236268
959034 | [N] C - W Main (Trunk) Emu Park West Reservoir | 3846983 |  |  |  |  | 2 2013/2014: balances to submitted
959040 | [N] R - W Main Crossing QR Reserve Anniki St | 21983
987951 | [N] GWTP 4 x Endress & Hauser turbidity meters | 329741
987953 | [N] R GWTP No. 2 Sedimentation Tank 2 Instrumentation | 10992
987955 | [N] M No7 Dam WPS upgrade | 49460
Projects submitted but not approved in 2013-14 as at 08-05-12
984880 | [N] C-W-Reservoir West Emu Park | 2747845
959034 | [N] C - W Main (Trunk) Emu Park West Reservoir | 769396
Note on B76: Karyn Beck: Narratoin was 'R - W Gce Industrial 300mm Trunk Main
Note on B77: Karyn Beck: Narratoin was 'R - W Gce Industrial 300mm Trunk Main
Note on B90: Karyn Beck: Was narration '[N] R - W Gracemere ground level 10ML reservoir
Note on B92: Karyn Beck: Was narration '[N] R - W Gracemere ground level 10ML reservoir
Note on B93: Karyn Beck: Remove per advice from Phil McKone 08-11-11
Note on B99: Karyn Beck: Narratoin was 'R - W Gce Industrial 300mm Trunk Main

## Water (Repl.)
Water - Replacement Capital Works Program
[7 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[6 empty] | Yr | 2011/2012 | 2012/2013 | 2013/2014 | 2014/2015 | 2015/2016 | 2016/2017 | 2017/2018 | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | 2022/2023 | 2023/2024 | 2024/2025 | 2025/2026 | 2026/2027 | 2027/2028 | 2028/2029 | 2029/2030 | 2030/2031 | 2031/2032
| Project Category/Catchment | Proj. description | Est. Cost | Yr of Construction | Funding | Subsidy Available
|  |  | ($) |  |  | (%)
Identified Replacement Capital Works:
'0953346 | C - Water Reservoir Taranganbah Roof & Floor Res | Water | 1300000 | 2011 | CW1000000L300000 |  | 0 2011/2012: 1300000
'0958997 | C - Water Reservoir Emu Park Roof Investigation | Water | 30000 | 2011 | RES |  | 0 2011/2012: 30000
'0640299 | C W Main – Coast – Reticulation Renewal AC | Water | 865000 | 2011 | D131880RES500000L233120 |  | 0 2011/2012: 865000
0639365 | C - W Meter Replacement Program | Water | 80400 | 2011 | L45400D35000 |  | 0 2011/2012: 80400
0984419 | C - W V&H Replacement Program | Water | 20000 | 2011 | D |  | 0 2011/2012: 20000
'0641187 | C-W Hobas Trunk Main Replacement | Water | 1780000 | 2011 | D9605RES783955L986440 |  | 0 2011/2012: 1780000
'0959005 | C - WTP Yeppoon PLC & Comms | Water | 425000 | 2011 | RES350000L75000 |  | 0 2011/2012: 425000
'0959008 | C - W Emu Park Reservoir Altitude valve removal | Water | 5000 | 2011 | L |  | 0 2011/2012: 5000
'0581020 | M-W Main-Mt Morgan-Reticulation Renewal AC | Water | 675000 | 2011 | DEPN |  | 0 2011/2012: 675000
'0581074 | M-W-Meter Replacement | Water | 2000 | 2011 | L |  | 0 2011/2012: 2000
'0580996 | R-W-V&H Maintenance Program | Water | 10000 | 2011 | DEPN |  | 0 2011/2012: 10000
0984421 | Marl - W V&H Replacement Program | Water | 20000 | 2011 | DEPN |  | 0 2011/2012: 20000
0943005 | R - W Mt Charlton Reservoir Refurb | Water | 320000 | 2011 | CWW |  | 0 2011/2012: 320000
'0581085 | R-W-Barrage Rton Crane Restore | Water | 5000 | 2011 | L |  | 0 2011/2012: 5000
'0581086 | R-W-Barrage Rton Gate Winch Cables | Water | 88700 | 2011 | L |  | 0 2011/2012: 88700
'0640316 | R-W-Barrage Rton Gates Refurbishment | Water | 257000 | 2011 | L47031RES209969 |  | 0 2011/2012: 257000
0986576 | [R] R - W Barrage Upgrade & Refurbishmen | Water | 150000 | 2011 | D |  | 0 2011/2012: 150000
0986577 | [R] R - W Barrage Physical Security Upgr | Water | 65000 | 2011 | D |  | 0 2011/2012: 65000
'0581078 | R -W-Main Replacement Reticulation | Water | 3750000 | 2011 | DEPN |  | 0 2011/2012: 3750000
'0640307 | R-W-Main Mt Charlton Refurbish Steel Pipeline | Water | 20000 | 2011 | L |  | 0 2011/2012: 20000
'0581081 | R-W-Meter Replacement | Water | 8000 | 2011 | L |  | 0 2011/2012: 8000
'0580999 | R-W-Meters Gmere | Water | 5000 | 2011 | RES |  | 0 2011/2012: 5000
0959189 | R - W GWTP Chlorinator Upgrade | Water | 42000 | 2011 | L |  | 0 2011/2012: 42000
0959173 | R - W GWTP Sedimentation Tank 1 Instrume | Water | 3310 | 2011 | L |  | 0 2011/2012: 3310
0959185 | R - W GWTP Outflow Water Instrumentation | Water | 4046.9 | 2011 | L |  | 0 2011/2012: 4046.9
0959188 | R - W GWTP Filter Outlet Valve Upgrade | Water | 6185 | 2011 | L |  | 0 2011/2012: 6185
0581041 | R-W-Barrage Rton Gate Seal Rehabilitation | Water | 0 | 2011 | L |  | 0 2011/2012: 0
0581050 | R - WPS Highlift & lowlift Replace emergency breakers | Water | 15000 | 2011 | L |  | 0 2011/2012: 15000
0583067 | R - Water PS Yaamba Rd Replacement works | Water | 20600 | 2011 | L |  | 0 2011/2012: 20600
0581152 | M - Water Reservoir North Repairs Power | Water | 57513.67 | 2011 | L |  | 0 2011/2012: 57513.67
0637118 | Fletchers Creek WPS Switchboard and asso | Water | 11700 | 2011 | L |  | 0 2011/2012: 11700
0581039 | C - Water PS Taranganbah High Zone | Water | 11000 | 2011 | RES |  | 0 2011/2012: 11000
0954358 | O - WPS Montrose Ck & Dempsey St - Repla | Water | 26446 | 2011 | DEPN5000L21446 |  | 0 2011/2012: 26446
'0959002 | R-W-Forbes Ave Pump Stn Electrical | Water | 0 | 2011 | L |  | 0 2011/2012: 0
'0959003 | ML - W Marlborough Bore Pumps Replacement | Water | 10400 | 2011 | DEPN |  | 0 2011/2012: 10400
958998 | [R] C - W Emu Park Reservoir Wall Restoration | Water | 82345 | 2012 |  |  | 1 2012/2013: 82345
959005 | [R] C - WTP Yeppoon PLC & Comms | Water | 527587 | 2012 |  |  | 1 2012/2013: 527587
987954 | [R] C Waterpark Ck Lowlift screen renewal | Water | 10991 | 2012 |  |  | 1 2012/2013: 10991
641187 | [R] C-W Main (Trunk) Hobas Replacement | Water | 1000000 | 2012 |  |  | 1 2012/2013: 1000000
581020 | [R] M - Water Main Replacement Program | Water | 741918 | 2012 |  |  | 1 2012/2013: 741918
581074 | [R] M-W-Meter Replacement | Water | 5496 | 2012 |  |  | 1 2012/2013: 5496
959009 | [R] R - W GWTP Highlift pump staton upgrade | Water | 2500000 | 2012 |  |  | 1 2012/2013: 2500000
987952 | [R] R Glenmore Lowlift WPS Switchboard Upgrade | Water | 274785 | 2012 |  |  | 1 2012/2013: 274785
581078 | [R] R -Water Main Replacement Program | Water | 2897414 | 2012 |  |  | 1 2012/2013: 2897414
988096 | [R] R-W V&H City Refurbishment Program | Water | 54957 | 2012 |  |  | 1 2012/2013: 54957
984990 | [R] R-W-Meters Gmere | Water | 9982 | 2012 |  |  | 1 2012/2013: 9982
943005 | [R] R-WPS and Reservoir Caves | Water | 63793 | 2012 |  |  | 1 2012/2013: 63793
641498 | [R] R-W-Reservoir Lucas St Gce Replace pump controls | Water | 14043 | 2012 |  |  | 1 2012/2013: 14043
581081 | [R] Water Meter Replacement Rockhampton | Water | 38470 | 2012 |  |  | 1 2012/2013: 38470
987644 | [R] C - W Replace 200 dia PVC Mains Vin E Jones & Pacific Hts Dr | Water | 307758 | 2013 |  |  | 2 2013/2014: 307758
581041 | [R] R - Water Barrage Gate Seal Rehabilitation | Water | 573707 | 2013 |  |  | 2 2013/2014: 573707
640307 | [R] W Mt Charlton Steel MA Maintenance | Water | 82435 | 2013 |  |  | 2 2013/2014: 82435
641187 | [R] C-W Main (Trunk) Hobas Replacement | Water | 648708 | 2013 |  |  | 2 2013/2014: 648708
581020 | [R] M - Water Main Replacement Program | Water | 741918 | 2013 |  |  | 2 2013/2014: 741918
959009 | [R] R - W GWTP Highlift pump staton upgrade | Water | 1747845 | 2013 |  |  | 2 2013/2014: 1747845
581078 | [R] R -Water Main Replacement Program | Water | 4250678 | 2013 |  |  | 2 2013/2014: 4250678
581081 | [R] Water Meter Replacement Rockhampton | Water | 38470 | 2013 |  |  | 2 2013/2014: 38470
988096 | [R] R-W V&H City Refurbishment Program | Water | 54957 | 2013 |  |  | 2 2013/2014: 54957
984990 | [R] R-W-Meters Gmere | Water | 21982 | 2013 |  |  | 2 2013/2014: 21982
984991 | [R] M-W-Meter Replacement | Water | 5496 | 2013 |  |  | 2 2013/2014: 5496
640307 | [R] W Mt Charlton Steel MA Maintenance | Water | 82435 | 2013 |  |  | 2 2013/2014: 82435
640316 | [R] Water Barrage Gates Maintenance | Water | 219828 | 2014 |  |  | 3 2014/2015: 219828
581078 | [R] R -Water Main Replacement Program | Water | 7630786 | 2014 |  |  | 3 2014/2015: 7630786
581020 | [R] M - Water Main Replacement Program | Water | 186854 | 2014 |  |  | 3 2014/2015: 186854
581041 | [R] R - Water Barrage Gate Seal Rehabilitation | Water | 549000 | 2014 |  |  | 3 2014/2015: 549000
640307 | [R] W Mt Charlton Steel MA Maintenance | Water | 82435 | 2014 |  |  | 3 2014/2015: 82435
581081 | [R] Water Meter Replacement Rockhampton | Water | 38470 | 2014 |  |  | 3 2014/2015: 38470
988096 | [R] R-W V&H City Refurbishment Program | Water | 54957 | 2014 |  |  | 3 2014/2015: 54957
984990 | [R] R-W-Meters Gmere | Water | 21982 | 2014 |  |  | 3 2014/2015: 21982
984991 | [R] M-W-Meter Replacement | Water | 5496 | 2014 |  |  | 3 2014/2015: 5496
| C-WTP | Water | 37800 | 2015 |  |  | 4 2015/2016: 37800
| M-W-Main Reticulation Renewal AC | Water | 170000 | 2015 |  |  | 4 2015/2016: 170000
| M-W-Meter Replacement | Water | 18000 | 2015 |  |  | 4 2015/2016: 18000
| O-W-Main Reticulation Renewal Galvanised & Poly Pipe | Water | 70000 | 2015 |  |  | 4 2015/2016: 70000
| R-WPS | Water | 18292 | 2015 |  |  | 4 2015/2016: 18292
| R-WPS & Reservoir Caves | Water | 19176 | 2015 |  |  | 4 2015/2016: 19176
| R-WTP Glenmore | Water | 414417 | 2015 |  |  | 4 2015/2016: 414417
| R-W-Barrage Rton Gate Guides | Water | 400000 | 2015 |  |  | 4 2015/2016: 400000
| R-W-Barrage Rton Gates | Water | 100000 | 2015 |  |  | 4 2015/2016: 100000
| R-W-Main Mild Steel | Water | 75000 | 2015 |  |  | 4 2015/2016: 75000
| R-W-Meter Replacement | Water | 372755 | 2015 |  |  | 4 2015/2016: 372755
| R-W-Meters Gmere | Water | 74971 | 2015 |  |  | 4 2015/2016: 74971
| R-W-V&H Maintenance Program | Water | 50000 | 2015 |  |  | 4 2015/2016: 50000
| W-Main Replacement Reticulation | Water | 4500000 | 2015 |  |  | 4 2015/2016: 4500000
| C-W-Dam Kellys Offstream Storage | Water | 50000 | 2016 |  |  | 5 2016/2017: 50000
| M-W-Main Reticulation Renewal AC | Water | 170000 | 2016 |  |  | 5 2016/2017: 170000
| M-W-Meter Replacement | Water | 18000 | 2016 |  |  | 5 2016/2017: 18000
| O-W-Main Reticulation Renewal Galvanised & Poly Pipe | Water | 70000 | 2016 |  |  | 5 2016/2017: 70000
| R-W-Barrage Rton Gate Guides | Water | 400000 | 2016 |  |  | 5 2016/2017: 400000
| R-W-Barrage Rton Gates | Water | 100000 | 2016 |  |  | 5 2016/2017: 100000
| R-W-Main Mild Steel | Water | 75000 | 2016 |  |  | 5 2016/2017: 75000
| R-W-Meter Replacement | Water | 219622 | 2016 |  |  | 5 2016/2017: 219622
| R-W-Meters Gmere | Water | 74971 | 2016 |  |  | 5 2016/2017: 74971
| R-W-Nerimbera – Water Reticulation Upgrade | Water | 140000 | 2016 |  |  | 5 2016/2017: 140000
| R-W-V&H Maintenance Program | Water | 50000 | 2016 |  |  | 5 2016/2017: 50000
| W-Main Replacement Reticulation | Water | 4500000 | 2016 |  |  | 5 2016/2017: 4500000
| R-WPS | Water | 47254 | 2016 |  |  | 5 2016/2017: 47254
| R-W-Reservoir | Water | 169201 | 2016 |  |  | 5 2016/2017: 169201
| R-WTP Glenmore | Water | 12195 | 2016 |  |  | 5 2016/2017: 12195
| M-W-Main Reticulation Renewal AC | Water | 170000 | 2017 |  |  | 6 2017/2018: 170000
| M-W-Meter Replacement | Water | 18000 | 2017 |  |  | 6 2017/2018: 18000
| O-W-Main Reticulation Renewal Galvanised & Poly Pipe | Water | 70000 | 2017 |  |  | 6 2017/2018: 70000
| R-W-Barrage Rton Gate Guides | Water | 400000 | 2017 |  |  | 6 2017/2018: 400000
| R-W-Barrage Rton Gates | Water | 100000 | 2017 |  |  | 6 2017/2018: 100000
| R-W-Main Mild Steel | Water | 75000 | 2017 |  |  | 6 2017/2018: 75000
| R-W-Reservoir | Water | 15243 | 2017 |  |  | 6 2017/2018: 15243
| R-WPS | Water | 12195 | 2017 |  |  | 6 2017/2018: 12195
| R-W-Meter Replacement | Water | 200000 | 2017 |  |  | 6 2017/2018: 200000
| R-W-Meters Gmere | Water | 74971 | 2017 |  |  | 6 2017/2018: 74971
| R-W-V&H Maintenance Program | Water | 50000 | 2017 |  |  | 6 2017/2018: 50000
| R-W-Main Replacement Reticulation | Water | 4500000 | 2017 |  |  | 6 2017/2018: 4500000
| Marl-WPS & Reservoir | Water | 21780 | 2017 |  |  | 6 2017/2018: 21780
| M-W-Main Reticulation Renewal AC | Water | 170000 | 2018 |  |  | 7 2018/2019: 170000
| M-W-Meter Replacement | Water | 18000 | 2018 |  |  | 7 2018/2019: 18000
| O-W-Main Reticulation Renewal Galvanised & Poly Pipe | Water | 70000 | 2018 |  |  | 7 2018/2019: 70000
| R-W-Reservoir | Water | 15243 | 2018 |  |  | 7 2018/2019: 15243
| R-WTP Glenmore | Water | 60973 | 2018 |  |  | 7 2018/2019: 60973
| R-W-Barrage Rton Gates | Water | 100000 | 2018 |  |  | 7 2018/2019: 100000
| R-W-Meter Replacement | Water | 200000 | 2018 |  |  | 7 2018/2019: 200000
| R-W-Meters Gmere | Water | 74971 | 2018 |  |  | 7 2018/2019: 74971
| R-W-V&H Maintenance Program | Water | 50000 | 2018 |  |  | 7 2018/2019: 50000
| W-Main Replacement Reticulation | Water | 4500000 | 2018 |  |  | 7 2018/2019: 4500000
| R-WPS & Reservoir Caves | Water | 10262 | 2018 |  |  | 7 2018/2019: 10262
| C-W- Reservoir Sites Emu Park | Water | 96905 | 2018 |  |  | 7 2018/2019: 96905
| C-WTP | Water | 314268 | 2018 |  |  | 7 2018/2019: 314268
| R-W-Barrage Rton Gates | Water | 100000 | 2019 |  |  | 8 2019/2020: 100000
| R-W-Meter Replacement | Water | 200000 | 2019 |  |  | 8 2019/2020: 200000
| O-W-Main Reticulation Renewal Galvanised & Poly Pipe | Water | 70000 | 2019 |  |  | 8 2019/2020: 70000
| W-Main Replacement Reticulation | Water | 1119000 | 2019 |  |  | 8 2019/2020: 1119000
| R-W-Parkhurst Ind Est Reservoir CHEMICAL NaOCl Building | Water | 20000 | 2019 |  |  | 8 2019/2020: 20000
| R-W-Parkhurst Ind Est Reservoir Pumps/Pipework/Instrumentation/Valves | Water | 54862.79 | 2019 |  |  | 8 2019/2020: 54862.79
| C-W-Kelly's Off Stream Storage Pump Station - Telemetry | Water | 296268.54 | 2019 |  |  | 8 2019/2020: 296268.54
| CA-W-Mt Charlton Pipework and Valves | Water | 332886 | 2019 |  |  | 8 2019/2020: 332886
| M-W-Main PRVs Reticulation | Water | 5000 | 2020 |  |  | 9 2020/2021: 5000
| R-W-Barrage Rton Gates | Water | 100000 | 2020 |  |  | 9 2020/2021: 100000
| R-W-Main Mild Steel | Water | 481544 | 2020 |  |  | 9 2020/2021: 481544
| R-W-Main PVC | Water | 132333 | 2020 |  |  | 9 2020/2021: 132333
| R-W-Meter Replacement | Water | 200000 | 2020 |  |  | 9 2020/2021: 200000
| R-W-Meters Gmere | Water | 3160 | 2020 |  |  | 9 2020/2021: 3160
| W-Main Replacement Reticulation | Water | 1261645 | 2020 |  |  | 9 2020/2021: 1261645
| *uPVC Watermain (50 dia Carbeen St) | Water | 34938.86 | 2020 |  |  | 9 2020/2021: 34938.86
| *Braddy St ELECTRICAL EQUIPMENT INSTRUMENTATION | Water | 71645.7 | 2020 |  |  | 9 2020/2021: 71645.7
| *Grouted stone pitched drains, in place (Barrage) | Water | 16372 | 2020 |  |  | 9 2020/2021: 16372
| *Rock filled wire mats, in place (Barrage) | Water | 788020 | 2020 |  |  | 9 2020/2021: 788020
| *Backup Booster Pump Number One - Marlborough | Water | 12337.93 | 2020 |  |  | 9 2020/2021: 12337.93
| *Bore Pump Number One - Marlborough | Water | 14871.96 | 2020 |  |  | 9 2020/2021: 14871.96
| *Bore Pump Number Two - Marlborough | Water | 14871.96 | 2020 |  |  | 9 2020/2021: 14871.96
| M-W-Main PRVs Reticulation | Water | 20000 | 2021 |  |  | 10 2021/2022: 20000
| R-W Property Services Replacement | Water | 1119000 | 2021 |  |  | 10 2021/2022: 1119000
| R-W-Barrage Rton Gates | Water | 100000 | 2021 |  |  | 10 2021/2022: 100000
| R-W-Meter Replacement | Water | 200000 | 2021 |  |  | 10 2021/2022: 200000
| R-W Property Services Replacement | Water | 1119000 | 2022 |  |  | 11 2022/2023: 1119000
| R-W-Barrage Rton Gates | Water | 100000 | 2022 |  |  | 11 2022/2023: 100000
| R-W-Main Replace Long Services (Galv/Cl) <100 Diameter | Water | 94860 | 2022 |  |  | 11 2022/2023: 94860
| R-W-Meter Replacement | Water | 203695 | 2022 |  |  | 11 2022/2023: 203695
| R-W-Meters Gmere | Water | 2370 | 2022 |  |  | 11 2022/2023: 2370
| R-W Property Services Replacement | Water | 1119000 | 2023 |  |  | 12 2023/2024: 1119000
| R-W-Barrage Rton Gates | Water | 100000 | 2023 |  |  | 12 2023/2024: 100000
| R-W-Main Replace Long Services (Galv/Cl) <100 Diameter | Water | 30144 | 2023 |  |  | 12 2023/2024: 30144
| R-W-Meters Gmere | Water | 1185 | 2023 |  |  | 12 2023/2024: 1185
| R-W Property Services Replacement | Water | 1119000 | 2024 |  |  | 13 2024/2025: 1119000
| R-W-Barrage Rton Gates | Water | 100000 | 2024 |  |  | 13 2024/2025: 100000
| R-W-Main Replace Long Services (Galv/Cl) <100 Diameter | Water | 6020 | 2024 |  |  | 13 2024/2025: 6020
| R-W-Meters Gmere | Water | 395 | 2024 |  |  | 13 2024/2025: 395
| R-WPS | Water | 27438 | 2024 |  |  | 13 2024/2025: 27438
| R-W-Reservoir | Water | 15243 | 2024 |  |  | 13 2024/2025: 15243
| R-WTP Glenmore | Water | 285416 | 2024 |  |  | 13 2024/2025: 285416
| M-WPS-Main Black St Reticulation | Water | 12000 | 2025 |  |  | 14 2025/2026: 12000
| M-W-Pumps Booster | Water | 6000 | 2025 |  |  | 14 2025/2026: 6000
| R-W Property Services Replacement | Water | 1119000 | 2025 |  |  | 14 2025/2026: 1119000
| R-W-Barrage Rton Gates | Water | 100000 | 2025 |  |  | 14 2025/2026: 100000
| R-W-Main Replace Long Services (Galv/Cl) <100 Diameter | Water | 15403 | 2025 |  |  | 14 2025/2026: 15403
| R-W-Meters Gmere | Water | 395 | 2025 |  |  | 14 2025/2026: 395
| R-WPS | Water | 65546 | 2025 |  |  | 14 2025/2026: 65546
| R-WTP Glenmore | Water | 293107 | 2025 |  |  | 14 2025/2026: 293107
| M-W-Main Reticulation Chlorination | Water | 2500 | 2026 |  |  | 15 2026/2027: 2500
| R-W Property Services Replacement | Water | 1119000 | 2026 |  |  | 15 2026/2027: 1119000
| R-W-Main Replace Long Services (Galv/Cl) <100 Diameter | Water | 1728 | 2026 |  |  | 15 2026/2027: 1728
| R-WPS | Water | 133967 | 2026 |  |  | 15 2026/2027: 133967
| R-WTP Glenmore | Water | 80790 | 2026 |  |  | 15 2026/2027: 80790
| R-W Property Services Replacement | Water | 1119000 | 2027 |  |  | 16 2027/2028: 1119000
| R-WPS | Water | 18292 | 2027 |  |  | 16 2027/2028: 18292
| R-WTP Glenmore | Water | 109752 | 2027 |  |  | 16 2027/2028: 109752
| R-W Property Services Replacement | Water | 1119000 | 2028 |  |  | 17 2028/2029: 1119000
| R-W-Main Replace Long Services (Galv/Cl) <100 Diameter | Water | 28408 | 2028 |  |  | 17 2028/2029: 28408
| R-W-Meters district & PRVs | Water | 30206 | 2028 |  |  | 17 2028/2029: 30206
| R-WPS | Water | 22865 | 2028 |  |  | 17 2028/2029: 22865
| M-W-Pumps Booster | Water | 20000 | 2029 |  |  | 18 2029/2030: 20000
| R-W-Main Replace Long Services (Galv/Cl) <100 Diameter | Water | 10761 | 2029 |  |  | 18 2029/2030: 10761
| R-WPS Gmere Lucas St Booster | Water | 18185 | 2029 |  |  | 18 2029/2030: 18185
| R-W-Reservoir | Water | 57116 | 2029 |  |  | 18 2029/2030: 57116
| R-WTP Glenmore | Water | 64022 | 2029 |  |  | 18 2029/2030: 64022
| R-W-Main Mild Steel | Water | 413142 | 2030 |  |  | 19 2030/2031: 413142
| R-W-Main Replace Long Services (Galv/Cl) <100 Diameter | Water | 50325 | 2030 |  |  | 19 2030/2031: 50325
| R-WPS | Water | 179979 | 2030 |  |  | 19 2030/2031: 179979
| R-W-Main Replace Long Services (Galv/Cl) <100 Diameter | Water | 6538 | 2031 |  |  | 20 2031/2032: 6538
| R-W-Meters district & PRVs | Water | 21095 | 2031 |  |  | 20 2031/2032: 21095
| R-WPS | Water | 3172 | 2031 |  |  | 20 2031/2032: 3172
| R-W-Reservoir Mawdesley Hill | Water | 4000 | 2031 |  |  | 20 2031/2032: 4000
| R-WTP Glenmore | Water | 64302 | 2031 |  |  | 20 2031/2032: 64302
| M-WPS-Main Black St Reticulation | Water | 3000 | 2032
| R-W-Main AC Pipe | Water | 2596280 | 2032
| R-W-Main Replace Long Services (Galv/Cl) <100 Diameter | Water | 5421 | 2032
| R-W-Main Trunk | Water | 32390 | 2032
| R-WPS | Water | 52008 | 2032
| Total Proposed Replacement Works |  | 79552963.31 |  |  |  | 10089301.57 | 8221781 | 8556389 | 8789808 | 6320411 | 6096243 | 5707189 | 5680622 | 2193017.33 | 3136740.41 | 1439000 | 1519925 | 1250329 | 1553512 | 1611451 | 1337985 | 1247044 | 1200479 | 170084 | 643446 | 99107
|  |  | 76863864.31 | **this is years 2031 & 2032
Projects submitted but not approved in 2012-13 as at 08-05-12
987954 | [R] C Waterpark Ck Lowlift screen renewal | 21982

## Sewer (Repl.)
Sewer - Replacement Capital Works Program
[7 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[6 empty] | Yr | 2011/2012 | 2012/2013 | 2013/2014 | 2014/2015 | 2015/2016 | 2016/2017 | 2017/2018 | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | 2022/2023 | 2023/2024 | 2024/2025 | 2025/2026 | 2026/2027 | 2027/2028 | 2028/2029 | 2029/2030 | 2030/2031 | 2031/2032
| Project Category/Catchment | Proj. description | Est. Cost | Yr of Construction | Ave Useful Life | Subsidy Available
|  |  | ($) |  | (Yrs) | (%)
Identified Replacement Capital Works:
0640255 | C-S Communications & Automation | Sewer | 24000 | 2011 |  |  | 0 2011/2012: 24000
0959050 | C - SPS Wall St - 2 new pumps | Sewer | 11700 | 2011 |  |  | 0 2011/2012: 11700
0959045 | R - SPS Gme No4,5,6 Install Inlet Valves | Sewer | 28000 | 2011 |  |  | 0 2011/2012: 28000
0959211 | R - S Combined Line Replacement 62 Spencer - 2 Bishop | Sewer | 25000 | 2011 |  |  | 0 2011/2012: 25000
0959048 | C - SPS Ray Street Pump No1&2 | Sewer | 22900 | 2011 |  |  | 0 2011/2012: 22900
0943010 | C-SPS New SPS Impellers | Sewer | 0 | 2011 |  |  | 0 2011/2012: 0
0959046 | R - S SRTP Chlorinator Upgrade | Sewer | 35000 | 2011 |  |  | 0 2011/2012: 35000
0959054 | R - S NRSTP Concrete Refurb (weir gate wells) | Sewer | 23000 | 2011 |  |  | 0 2011/2012: 23000
0959051 | C - SPS Ray St Switchboard | Sewer | 93000 | 2011 |  |  | 0 2011/2012: 93000
0959052 | C - SPS Roslyn St Switchboard | Sewer | 0 | 2011 |  |  | 0 2011/2012: 0
0959053 | R - SPS No3 (Gce) Switchboard | Sewer | 93000 | 2011 |  |  | 0 2011/2012: 93000
0959055 | R - SPS Gme Old Capricorn Hwy No2 Electrical switchboard | Sewer | 93000 | 2011 |  |  | 0 2011/2012: 93000
0640877 | C - S Main Refurbishment (arising from r | Sewer | 116000 | 2011 |  |  | 0 2011/2012: 116000
0637914 | R - Sewer Refurbishment (arising from re | Sewer | 1541000 | 2011 |  |  | 0 2011/2012: 1541000
0954542 | C - STP Yeppoon Upgrade service water pu | Sewer | 100 | 2011 |  |  | 0 2011/2012: 100
0799975 | R - SPS North waste Inlet pipework upgrade | Sewer | 0 | 2011 |  |  | 0 2011/2012: 0
0959190 | R - STP South Aerator Installation | Sewer | 35700 | 2011 |  |  | 0 2011/2012: 35700
0966620 | R - SPS Arthur St Magnesium Install | Sewer | 11700 | 2011 |  |  | 0 2011/2012: 11700
0973931 | R - S NRWWTP Oxidation Ditchs Weir Actua | Sewer | 17400 | 2011 |  |  | 0 2011/2012: 17400
0581051 | R - SPS Arthur St New Air Extraction Sys | Sewer | 4000 | 2011 |  |  | 0 2011/2012: 4000
0974058 | R - NRSTP - Aerator replace 2x motors an | Sewer | 29570 | 2011 |  |  | 0 2011/2012: 29570
0581103 | C - S-Main Refurbish Reticulation | Sewer | 1314000 | 2011 |  |  | 0 2011/2012: 1314000
0581107 | R - S-Main Refurbish Reticulation | Sewer | 3370000 | 2011 |  |  | 0 2011/2012: 3370000
640877 | [R] C - S Main Refurbishment (arising from relining) | Sewer | 219828 | 2012 |  |  | 1 2012/2013: 219828
987654 | [R] C S Emu Park test infiltration at manholes | Sewer | 219828 | 2012 |  |  | 1 2012/2013: 219828
987937 | [R] C SPS Keppel St North Electrical Upgrade | Sewer | 28760 | 2012 |  |  | 1 2012/2013: 28760
987942 | [R] C STP Yeppoon Air Compressor | Sewer | 23966 | 2012 |  |  | 1 2012/2013: 23966
987941 | [R] C STP Yeppoon SCADA computer upgrade | Sewer | 9586 | 2012 |  |  | 1 2012/2013: 9586
640255 | [R] C-S Communications & Automation | Sewer | 36272 | 2012 |  |  | 1 2012/2013: 36272
987944 | [R] M STP Chlorination Upgrade | Sewer | 11983 | 2012 |  |  | 1 2012/2013: 11983
987927 | [R] R SPS Arthur St electrical upgrade | Sewer | 191730 | 2012 |  |  | 1 2012/2013: 191730
987943 | [R] R SPS Gracemere Duckponds Irrigation Electrical Upgrade | Sewer | 71899 | 2012 |  |  | 1 2012/2013: 71899
987929 | [R] R SPS Kalka Shades electrical upgrade | Sewer | 28760 | 2012 |  |  | 1 2012/2013: 28760
987930 | [R] R STP North Rockhampton inlet screen | Sewer | 57519 | 2012 |  | 0 | 1 2012/2013: 57519
987931 | [R] R STP North Rockhampton aerator replacement | Sewer | 45536 | 2012 |  |  | 1 2012/2013: 45536
987932 | [R] R STP South Rockhampton Safety Upgrade | Sewer | 21569 | 2012 |  |  | 1 2012/2013: 21569
581107 | [R] Sewer Main Relining & associated works | Sewer | 1648707 | 2012 |  |  | 1 2012/2013: 1648707
987928 | [R] R SPS East Lane SPS electrical upgrade | Sewer | 28760 | 2013 |  |  | 2 2013/2014: 28760
640877 | [R] C - S Main Refurbishment (arising from relining) | Sewer | 219828 | 2013 |  |  | 2 2013/2014: 219828
987654 | [R] C S Emu Park test infiltration at manholes | Sewer | 219828 | 2013 |  |  | 2 2013/2014: 219828
987938 | [R] C SPS Keppel St South Electrical Upgrade | Sewer | 28760 | 2013 |  |  | 2 2013/2014: 28760
987940 | [R] C SPS Emu Park Rockhampton Rd Pump Upgrade | Sewer | 28760 | 2013 |  |  | 2 2013/2014: 28760
987939 | [R] C SPS Kennedy St Electrical Upgrade | Sewer | 28760 | 2013 |  |  | 2 2013/2014: 28760
987936 | [R] C SPS Rosslyn Bay Marina Electrical Upgrade | Sewer | 28760 | 2013 |  |  | 2 2013/2014: 28760
640255 | [R] C-S Communications & Automation | Sewer | 36272 | 2013 |  |  | 2 2013/2014: 36272
581103 | [R] MAINS - CC - Sewer Retic AC Yeppoon (reline following camera inspection) | Sewer | 549569 | 2013 |  |  | 2 2013/2014: 549569
581103 | [R] MAINS - CC - Sewer Retic AC Yeppoon (reline following camera inspection) | Sewer | 549569 | 2013 |  |  | 2 2013/2014: 549569
637914 | [R] R - Sewer Refurbishment (arising from relining contract) | Sewer | 2198276 | 2013 |  |  | 2 2013/2014: 2198276
637914 | [R] R - Sewer Refurbishment (arising from relining contract) | Sewer | 2398276 | 2013 |  |  | 2 2013/2014: 2398276
581107 | [R] Sewer Main Relining & associated works | Sewer | 1648707 | 2013 |  |  | 2 2013/2014: 1648707
581068 | [R] STP North Upgrade Switchboards in No1 & No2 SPS | Sewer | 219828 | 2013 |  |  | 2 2013/2014: 219828
640877 | [R] C - S Main Refurbishment (arising from relining) | Sewer | 153879 | 2014 |  |  | 3 2014/2015: 153879
640255 | [R] C-S Communications & Automation | Sewer | 36272 | 2014 |  |  | 3 2014/2015: 36272
581103 | [R] MAINS - CC - Sewer Retic AC Yeppoon (reline following camera inspection) | Sewer | 549569 | 2014 |  |  | 3 2014/2015: 549569
637914 | [R] R - Sewer Refurbishment (arising from relining contract) | Sewer | 2998276 | 2014 |  |  | 3 2014/2015: 2998276
581107 | [R] Sewer Main Relining & associated works | Sewer | 1648707 | 2014 |  |  | 3 2014/2015: 1648707
0984912 | [R] C-STP Decommission old STP | Sewer | 400000 | 2015 |  |  | 4 2015/2016: 400000
0984913 | [R] C-STP Decommission old STP (S031) | Sewer | 200000 | 2015 |  |  | 4 2015/2016: 200000
0581107 | R - S-Main Refurbish Reticulation | Sewer | 3448820 | 2015 |  |  | 4 2015/2016: 3448820
0990022 | [R] R-SPS | Sewer | 11785 | 2015 |  |  | 4 2015/2016: 11785
0984916 | [R] C-SPS Ypn | Sewer | 39240 | 2015 |  |  | 4 2015/2016: 39240
0640877 | C - S-Main Refurbish Reticulation | Sewer | 100000 | 2015 |  |  | 4 2015/2016: 100000
0640877 | C - S-Main Refurbish Reticulation | Sewer | 100000 | 2016 |  |  | 5 2016/2017: 100000
0984916 | [R] C-SPS Ypn | Sewer | 18900 | 2016 |  |  | 5 2016/2017: 18900
0581107 | R - S-Main Refurbish Reticulation | Sewer | 4780919 | 2016 |  |  | 5 2016/2017: 4780919
0984908 | [R] R-S-Main Raising | Sewer | 13881 | 2016 |  |  | 5 2016/2017: 13881
0984938 | [R] R-STP Rton North | Sewer | 78864 | 2016 |  |  | 5 2016/2017: 78864
0990022 | [R] R-SPS | Sewer | 158406 | 2016 |  |  | 5 2016/2017: 158406
0581107 | R - S-Main Refurbish Reticulation | Sewer | 6122431 | 2017 |  |  | 6 2017/2018: 6122431
0640877 | C - S-Main Refurbish Reticulation | Sewer | 100000 | 2017 |  |  | 6 2017/2018: 100000
0990022 | [R] R-SPS | Sewer | 11785 | 2017 |  |  | 6 2017/2018: 11785
0984937 | [R] C-SPS Emu Park | Sewer | 18900 | 2017 |  |  | 6 2017/2018: 18900
0984916 | [R] C-SPS Ypn | Sewer | 128220 | 2017 |  |  | 6 2017/2018: 128220
0581107 | R - S-Main Refurbish Reticulation | Sewer | 6748357 | 2018 |  |  | 7 2018/2019: 6748357
0640877 | C - S-Main Refurbish Reticulation | Sewer | 100000 | 2018 |  |  | 7 2018/2019: 100000
0984954 | [R] C-S-Main Yeppoon Rising | Sewer | 284710 | 2018 |  |  | 7 2018/2019: 284710
0990022 | [R] R-SPS | Sewer | 39776 | 2018 |  |  | 7 2018/2019: 39776
0984916 | [R] C-SPS Ypn | Sewer | 25878 | 2018 |  |  | 7 2018/2019: 25878
0984955 | [R] C-S-Main Adelaide Park Gravity Trunk | Sewer | 302000 | 2020 |  |  | 9 2020/2021: 302000
0990022 | [R] R-SPS | Sewer | 5258 | 2021 |  |  | 10 2021/2022: 5258
| R-STP | Sewer | 109115 | 2021 |  |  | 10 2021/2022: 109115
| R-SPS | Sewer | 160678 | 2024 |  |  | 13 2024/2025: 160678
| R-S-Reuse Scheme | Sewer | 2640 | 2024 |  |  | 13 2024/2025: 2640
| R-STP | Sewer | 253307 | 2024 |  |  | 13 2024/2025: 253307
| R-STP | Sewer | 27517 | 2025 |  |  | 14 2025/2026: 27517
| R-STP | Sewer | 10800 | 2026 |  |  | 15 2026/2027: 10800
| R-STP | Sewer | 3606 | 2027 |  |  | 16 2027/2028: 3606
| R-STP | Sewer | 37123 | 2030 |  |  | 19 2030/2031: 37123
| R-STP | Sewer | 10867 | 2031 |  |  | 20 2031/2032: 10867
| R-STP | Sewer | 56592 | 2032
| Total Proposed Replacement Works |  | 46985044 |  |  |  | 6888070 | 2615943 | 8183953 | 5386703 | 4199845 | 5150970 | 6381336 | 7198721 | 0 | 302000 | 114373 | 0 | 0 | 416625 | 27517 | 10800 | 3606 | 0 | 0 | 37123 | 10867
Projects submitted but not approved in 2012-13 as at 08-05-12
987928 | [R] R SPS East Lane SPS electrical upgrade | 57519
987930 | [R] R STP North Rockhampton inlet screen | 57519

## Sewer (New Works)
Sewer - NEW Capital Works Program
[7 empty] | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
[6 empty] | Yr | 2011/2012 | 2012/2013 | 2013/2014 | 2014/2015 | 2015/2016 | 2016/2017 | 2017/2018 | 2018/2019 | 2019/2020 | 2020/2021 | 2021/2022 | 2022/2023 | 2023/2024 | 2024/2025 | 2025/2026 | 2026/2027 | 2027/2028 | 2028/2029 | 2029/2030 | 2030/2031 | 2031/2032
| Project Category/Catchment | Proj. description | Est. Cost | Prop. Const.Date | Funding | Subsidy Available
|  |  | ($) |  |  | (%)
0959085 | R - Sewer Flow Loggers | Sewer | 45825 | 2011 |  |  | 0 2011/2012: 45825
0959064 | C - SPS Charles St Install new pumps | Sewer | 29000 | 2011 |  |  | 0 2011/2012: 29000
0959062 | C-SPS Kinka Area Stage 3 - Tenure | Sewer | 1670 | 2011 |  |  | 0 2011/2012: 1670
0959083 | R - S Network Overflow Monitoring Equipment | Sewer | 23000 | 2011 |  |  | 0 2011/2012: 23000
0959065 | C - S Main Jarman St Diversion | Sewer | 82000 | 2011 |  |  | 0 2011/2012: 82000
0943011 | C-S Ray St SPS new Valve Pit Valves and | Sewer | 33900 | 2011 |  |  | 0 2011/2012: 33900
0581134 | C - STP Emu Park Design & Construct | Sewer | 4452000 | 2011 |  |  | 0 2011/2012: 4452000
0978935 | C - Sewer Main (Gravity) 150mm - 9 Redman St to 33 Phillip St | Sewer | 175000 | 2011 |  |  | 0 2011/2012: 175000
0581005 | [N] C - Sewer Main (Gravity) Hidden Valley | Sewer | 40900 | 2011 |  |  | 0 2011/2012: 40900
0581003 | C - Sewer Main (Gravity) Reef St Design | Sewer | 117000 | 2011 |  |  | 0 2011/2012: 117000
0581093 | C - Sewer Main Kinka Stage 1 Design & C | Sewer | 152700 | 2011 |  |  | 0 2011/2012: 152700
0943021 | R- S Washpool Road gravity main Gce | Sewer | 969500 | 2011 |  |  | 0 2011/2012: 969500
0978950 | R- Sewer Main (Rising) Washpool Road Gce | Sewer | 126237 | 2011 |  |  | 0 2011/2012: 126237
0972935 | C - YSTP - New air compressor | Sewer | 18500 | 2011 |  |  | 0 2011/2012: 18500
0583033 | R - SPS Lucas St - Washpool St (design a | Sewer | 666100 | 2011 |  |  | 0 2011/2012: 666100
0583055 | R - Sewer Main (Gravity) 300mm Breakspear St (Gce) | Sewer | 290000 | 2011 |  |  | 0 2011/2012: 290000
0959061 | R - S NRSTP Effluent Reuse Scheme | Sewer | 0 | 2011 |  |  | 0 2011/2012: 0
0640281 | R-STPNorth Dewatering Biosolids | Sewer | 234000 | 2011 |  |  | 0 2011/2012: 234000
0943290 | C-STP Yeppoon Dewatering Facility | Sewer | 233000 | 2011 |  |  | 0 2011/2012: 233000
0640283 | R-STP Rton South (Pipeline from West Rton catchment) | Sewer | 117000 | 2011 |  |  | 0 2011/2012: 117000
0581121 | [U] C - Sewer Main (Rising) Cooee Bay Design of augmentation & duplication | Sewer | 2400 | 2011 |  |  | 0 2011/2012: 2400
0959072 | [N] C - S YSTP Augmentation Design & Construction | Sewer | 93000 | 2011 |  |  | 0 2011/2012: 93000
0581098 | C - SPS Statue Bay Augmentation | Sewer | 93000 | 2011 |  |  | 0 2011/2012: 93000
0640255 | C-S Communications & Automation | Sewer | 24000 | 2011 |  |  | 0 2011/2012: 24000
640281 | [N] R-STP North Dewatering Biosolids | Sewer | 677069 | 2012 |  |  | 1 2012/2013: 677069
943290 | [N] C - STP Yeppoon Dewatering Facility | Sewer | 518793 | 2012 |  |  | 1 2012/2013: 518793
959089 | [N] R - Misc Field Deployment System (DBYD/PTW) | Sewer | 274784 | 2012 |  |  | 1 2012/2013: 274784
959076 | [N] R - S Ramsay Cr SPS Rising Main - Tenure & Design | Sewer | 219828 | 2012 |  |  | 1 2012/2013: 219828
984903 | [N] C - SPS Tanby Heights Stage 1A to 1D (Committed Expenditure through Infrastructure Agreement) | Sewer | 206927 | 2012 |  |  | 1 2012/2013: 206927
984902 | [N] C-S-Main Hidden Valley Sewerage (Gravity Trunk, SPS & Rising Main) - design | Sewer | 76940 | 2012 |  |  | 1 2012/2013: 76940
959062 | [N] C - S Main Kinka Stage 3 Design | Sewer | 53121 | 2012 |  |  | 1 2012/2013: 53121
959079 | [N] C - SPS Kinka Area Stage 3 | Sewer | 32974 | 2012 |  |  | 1 2012/2013: 32974
959084 | [N] R - Misc CCTV Camera Unit | Sewer | 28760 | 2012 |  |  | 1 2012/2013: 28760
987933 | [N] R STP Gracemere STP Safety Upgrade | Sewer | 23966 | 2012 |  |  | 1 2012/2013: 23966
987934 | [N] R STP Microwave link to NRSTP and SRSTP | Sewer | 19172 | 2012 |  |  | 1 2012/2013: 19172
640255 | [R] C-S Communications & Automation | Sewer | 36271 | 2012 |  |  | 1 2012/2013: 36271
987937 | [R] C SPS Keppel St North Electrical Upgrade | Sewer | 28759 | 2012 |  |  | 1 2012/2013: 28759
987941 | [R] C STP Yeppoon SCADA computer upgrade | Sewer | 9586 | 2012 |  |  | 1 2012/2013: 9586
987944 | [R] M STP Chlorination Upgrade | Sewer | 11983 | 2012 |  |  | 1 2012/2013: 11983
987927 | [R] R SPS Arthur St electrical upgrade | Sewer | 191729 | 2012 |  |  | 1 2012/2013: 191729
987929 | [R] R SPS Kalka Shades electrical upgrade | Sewer | 28759 | 2012 |  |  | 1 2012/2013: 28759
987931 | [R] R STP North Rockhampton aerator replacement | Sewer | 45535 | 2012 |  |  | 1 2012/2013: 45535
987932 | [R] R STP South Rockhampton Safety Upgrade | Sewer | 21569 | 2012 |  |  | 1 2012/2013: 21569
987943 | [R] R SPS Gracemere Duckponds Irrigation Electrical Upgrade | Sewer | 71898 | 2012 |  |  | 1 2012/2013: 71898
987945 | [N] M STP Comms Upgrade | Sewer | 17256 | 2012 |  |  | 1 2012/2013: 17256
583055 | [U] Sewer Main (Trunk) Breakspeare St 300mm Gce | Sewer | 989224 | 2012 |  |  | 1 2012/2013: 989224
0984959 | [N] R- S Main (Gravity) 200mm (Gce) Industrial (relates to SPS17) - SEW 47 Gracemere Industrial Expansion | Sewer | 146185 | 2012 |  |  | 1 2012/2013: 146185
984960 | [N] R- S Main (Rising) 200mm (Gce) Industrial (relates to SPS17) | Sewer | 520991 | 2012 |  |  | 1 2012/2013: 520991
984949 | [N] R- S Main (Rising) 300mm (Gce) Industrial (relates to SPS16) | Sewer | 1538793 | 2012 |  |  | 1 2012/2013: 1538793
984925 | [N] R-SPS 16 (Gce) Industrial | Sewer | 406681 | 2012 |  |  | 1 2012/2013: 406681
984926 | [N] R-SPS 17 (Gce) Industrial | Sewer | 406681 | 2012 |  |  | 1 2012/2013: 406681
959212 | [U] R - S GSTP Augmentation | Sewer | 549569 | 2012 |  |  | 1 2012/2013: 549569
581121 | [U] C - Sewer Main (Rising) Cooee Bay Design of augmentation & duplication | Sewer | 1044181 | 2012 |  |  | 1 2012/2013: 1044181
987928 | [R] R SPS East Lane SPS electrical upgrade | Sewer | 28759 | 2013 |  |  | 2 2013/2014: 28759
959077 | [N] C - S Main Kinka Area Stage 3 Rising - Construction | Sewer | 23082 | 2013 |  |  | 2 2013/2014: 23082
987935 | [N] R Tools of trade vehicle Treatment and Supply | Sewer | 33553 | 2013 |  |  | 2 2013/2014: 33553
581005 | [N] C - Sewer Main (Gravity) Hidden Valley | Sewer | 54957 | 2013 |  |  | 2 2013/2014: 54957
987938 | [R] C SPS Keppel St South Electrical Upgrade | Sewer | 28759 | 2013 |  |  | 2 2013/2014: 28759
987648 | [U] R Glenmore Water Treatment plant amenities block | Sewer | 43966 | 2013 |  |  | 2 2013/2014: 43966
640255 | [R] C-S Communications & Automation | Sewer | 36271 | 2013 |  |  | 2 2013/2014: 36271
987936 | [R] C SPS Rosslyn Bay Marina Electrical Upgrade | Sewer | 28759 | 2013 |  |  | 2 2013/2014: 28759
987940 | [R] C SPS Emu Park Rockhampton Rd Pump Upgrade | Sewer | 28759 | 2013 |  |  | 2 2013/2014: 28759
987939 | [R] C SPS Kennedy St Electrical Upgrade | Sewer | 28759 | 2013 |  |  | 2 2013/2014: 28759
581068 | [R] STP North Upgrade Switchboards in No1 & No2 SPS | Sewer | 219828 | 2013 |  |  | 2 2013/2014: 219828
640283 | [N] R-STP Rton South (Pipeline from West Rton catchment) | Sewer | 549569 | 2013 |  |  | 2 2013/2014: 549569
640283 | [N] R-STP Rton South (Pipeline from West Rton catchment) | Sewer | 1099138 | 2013 |  |  | 2 2013/2014: 1099138
959070 | [N] C - S Main Tanby Rd South Rising | Sewer | 612220 | 2013 |  |  | 2 2013/2014: 612220
959061 | [N] S NRSTP Effluent Reuse Scheme | Sewer | 219828 | 2013 |  |  | 2 2013/2014: 219828
959078 | [N] C - S Main Tanby South Trunk Stage 3 - Design | Sewer | 475926 | 2013 |  |  | 2 2013/2014: 475926
959072 | [N] C - S YSTP Augmentation Design & Construction | Sewer | 2747845 | 2013 |  |  | 2 2013/2014: 2747845
959074 | [N] C - SPS Tanby Rd South - Design & Construct | Sewer | 355022 | 2013 |  |  | 2 2013/2014: 355022
959075 | [N] R - SPS Ramsay Cr Construction | Sewer | 460539 | 2013 |  |  | 2 2013/2014: 460539
988042 | [N] R Gce Main (Gravity) 300mm Ramsay Creek - SEW9 | Sewer | 268190 | 2013 |  |  | 2 2013/2014: 268190
988041 | [N] R Main (Rising) 200mm Ramsay Creek - SEW8 | Sewer | 305560 | 2013 |  |  | 2 2013/2014: 305560
987946 | [N] R S Main (Gravity) 300 mm Olive St (committed expenditure thru Ramsey Ck Infrastructure agreement) | Sewer | 268190 | 2013 |  |  | 2 2013/2014: 268190
959212 | [U] R - S GSTP Augmentation | Sewer | 4793233 | 2013 |  |  | 2 2013/2014: 4793233
959082 | [U] R - S Upgrade Trunk Cedric Archer Park | Sewer | 1868535 | 2013 |  |  | 2 2013/2014: 1868535
583055 | [U] Sewer Main (Trunk) Breakspeare St 300mm Gce | Sewer | 483621 | 2013 |  |  | 2 2013/2014: 483621
988043 | [N] R SEW11 | Sewer | 259396 | 2014 |  |  | 3 2014/2015: 259396
640255 | [R] C-S Communications & Automation | Sewer | 36271 | 2014 |  |  | 3 2014/2015: 36271
959072 | [N] C - S YSTP Augmentation Design & Construction | Sewer | 2747845 | 2014 |  |  | 3 2014/2015: 2747845
984919 | [N] C-S-Main (Rising) 200mm Farnborough Road Trunk | Sewer | 531983 | 2014 |  |  | 3 2014/2015: 531983
984904 | [N] C-SPS Charles Street | Sewer | 1035388 | 2014 |  |  | 3 2014/2015: 1035388
984907 | [N] C-SPS Farnborough Road PS#2 | Sewer | 912284 | 2014 |  |  | 3 2014/2015: 912284
984906 | [N] C-SPS Rockhampton - Emu Park Rd PS#1 | Sewer | 402284 | 2014 |  |  | 3 2014/2015: 402284
984958 | [N] R- S Main (Gravity) 200mm (Gce) Industrial (relates to SPS17) | Sewer | 292371 | 2014 |  |  | 3 2014/2015: 292371
640283 | [N] R-STP Rton South (Pipeline from West Rton catchment) | Sewer | 1099138 | 2014 |  |  | 3 2014/2015: 1099138
959212 | [U] R - S GSTP Augmentation | Sewer | 4793233 | 2014 |  |  | 3 2014/2015: 4793233
0984921 | [N] C-S-Main Kinka Stage 4 | Sewer | 46000 | 2015 | L/CW | 54228.6393 | 4 2015/2016: 46000
0984933 | [N] R - S Main (Gravity) 225mm Ramsay Ck (Westco) | Sewer | 158000 | 2015 | L/CW | 186263.5873 | 4 2015/2016: 158000
0984931 | [N] C-S-Main (Gravity) 300mm Farnborough Road Trunk | Sewer | 130000 | 2015 | L/CW | 153254.8503 | 4 2015/2016: 130000
0984920 | [N] C-SPS Tanby Rd (Yeppoon Ck) relates to Hidden Valley | Sewer | 300000 | 2015 | L/CW | 353665.0391 | 4 2015/2016: 300000
0984932 | [N] C- S Main (Rising) 200mm Tanby Rd (Yeppoon Ck) relates to Hidden Valley | Sewer | 147000 | 2015 | L/CW | 173295.8692 | 4 2015/2016: 147000
0984942 | [N] R-S-Main Fitzroy St Rising 300mm (Sth Rton STP Catchment) | Sewer | 320000 | 2015 | L/CW | 377242.7084 | 4 2015/2016: 320000
0984943 | [N] R-S-Main West St Rton Gravity Main Trunk 600mm (Sth Rton STP Catchment) | Sewer | 434000 | 2015 | L | 511635.4232 | 4 2015/2016: 434000
0984925 | [N] R-SPS 16 (Gce) Industrial | Sewer | 0 | 2015 | L/CW | 0 | 4 2015/2016: 0
0984949 | [N] R- S Main (Rising) 300mm (Gce) Industrial (relates to SPS16) | Sewer | 0 | 2015 | L/CW | 0 | 4 2015/2016: 0
0984926 | [N] R-SPS 17 (Gce) Industrial | Sewer | 0 | 2015 | L/CW | 0 | 4 2015/2016: 0
0984930 | [N] C-SPS Reef St PS#13 | Sewer | 270000 | 2015 | L/CW | 318298.5352 | 4 2015/2016: 270000
0984939 | [N] C-S-Main (Rising) 100mm Reef St | Sewer | 140000 | 2015 | L/CW | 165043.6849 | 4 2015/2016: 140000
0984941 | [N] C-S-Main (Gravity) 150mm Reef St | Sewer | 120000 | 2015 | L/CW | 141466.0156 | 4 2015/2016: 120000
0959072 | [N] C - S YSTP Augmentation Design & Construction | Sewer | 7000000 | 2015 | L | 8252184.2459 | 4 2015/2016: 7000000
0959212 | [U] R - S GSTP Augmentation | Sewer | 0 | 2015 | L | 0 | 4 2015/2016: 0
0984922 | [N] C - SPS Rosslyn St | Sewer | 130000 | 2015 | L/CW | 153254.8503 | 4 2015/2016: 130000
0984915 | [N] R - SPS Campbell St PS#3 | Sewer | 335000 | 2015 | L/CW | 394925.9603 | 4 2015/2016: 335000
0984934 | [N] C-S-Main (Gravity) 450mm Whitman St | Sewer | 272000 | 2015 | L/CW | 320656.3021 | 4 2015/2016: 272000
0984923 | [N] C-SPS Bell Park Emu Park East PS#2 | Sewer | 265000 | 2015 | L/CW | 312404.1179 | 4 2015/2016: 265000
0984936 | [N] C-S-Main (Gravity) 375mm Scenic Hwy | Sewer | 341000 | 2015 | L/CW | 401999.2611 | 4 2015/2016: 341000
0984944 | [N] R- S Main (Gravity) 450mm Armstrong St (Gce) | Sewer | 84000 | 2015 | L/CW | 99026.211 | 4 2015/2016: 84000
0984945 | [N] R- S Main (Gravity) 300mm Burke St | Sewer | 265000 | 2015 | L/CW | 312404.1179 | 4 2015/2016: 265000
0984946 | [N] R- S Main (Gravity) 400mm Parkhurst Industrial | Sewer | 431000 | 2015 | L/CW | 508098.7729 | 4 2015/2016: 431000
0984924 | [N] R-SPS Beak St (Gce) (Capricorn St PS#7to be replaced) | Sewer | 368000 | 2015 | L/CW | 433829.1146 | 4 2015/2016: 368000
0984952 | [N] C-S-Main (Rising) 150mm Bell Park Emu Park East from PS#2 | Sewer | 111000 | 2015 | L/CW | 130856.0645 | 4 2015/2016: 111000
0984953 | [N] C-S-Main Hidden Valley Sewerage (Retic) - construction | Sewer | 800000 | 2016 | L | 982717.2553 | 5 2016/2017: 800000
0984956 | [N] C-S-Main (Gravity) 225mm Tanby Road North | Sewer | 127000 | 2020 | L/CW | 183913.3231 | 9 2020/2021: 127000
0984958 | [N] R- S Main (Gravity) 200mm (Gce) Industrial (relates to SPS17) - SEW 46 Gracemere Industrial Expansion | Sewer | 0 | 2020 | L/CW | 0 | 9 2020/2021: 0
0984959 | [N] R- S Main (Gravity) 200mm (Gce) Industrial (relates to SPS17) - SEW 47 Gracemere Industrial Expansion | Sewer | 0 | 2020 | L/CW | 0 | 9 2020/2021: 0
0984960 | [N] R- S Main (Rising) 200mm (Gce) Industrial (relates to SPS17) | Sewer | 0 | 2020 | L/CW | 0 | 9 2020/2021: 0
0984964 | [N] R - SPS Edenbrook West | Sewer | 270000 | 2020 | L/CW | 390996.8286 | 9 2020/2021: 270000
0984965 | [N] R - S (Rising) 100mm Edenbrook West | Sewer | 149000 | 2020 | L/CW | 215772.3239 | 9 2020/2021: 149000
0984966 | [N] R - S Main (Gravity) 225mm Ramsay Ck (Westco) | Sewer | 110000 | 2020 | L/CW | 159295.0042 | 9 2020/2021: 110000
0984967 | [N] R-SPS Limestone Creek (SPS2) | Sewer | 323000 | 2020 | L/CW | 467748.0579 | 9 2020/2021: 323000
0984968 | [N] R - S Main (Rising) 300mm Limestone Ck | Sewer | 1036000 | 2020 | L/CW | 1500269.3127 | 9 2020/2021: 1036000
0984969 | [N] R - S Main (Gravity) 225mm Limestone Ck | Sewer | 158000 | 2020 | L/CW | 228805.5516 | 9 2020/2021: 158000
0984970 | [N] R - S Main (Gravity) 300mm Limestone Ck | Sewer | 105000 | 2020 | L/CW | 152054.3222 | 9 2020/2021: 105000
0984971 | [N] R - S Main (Gravity) 450mm Limestone Ck | Sewer | 258000 | 2020 | L/CW | 373619.1918 | 9 2020/2021: 258000
0984972 | [N] R - S Main (Gravity) 375mm Limestone Ck | Sewer | 519000 | 2020 | L/CW | 751582.7928 | 9 2020/2021: 519000
0984973 | [N] R - S Main (Gravity) 225mm Limestone Ck | Sewer | 63000 | 2020 | L/CW | 91232.5933 | 9 2020/2021: 63000
0984974 | [N] R - S Main (Gravity) 300mm Limestone Ck | Sewer | 126000 | 2020 | L/CW | 182465.1867 | 9 2020/2021: 126000
0984979 | [N] C-S-Main (Gravity) 300mm Hill St from Cap Green | Sewer | 374000 | 2020 | L/CW | 541603.0144 | 9 2020/2021: 374000
0984980 | [N] C-S-Main (Rising) 150mm Hill St from Cap Green | Sewer | 523000 | 2020 | L/CW | 757375.3384 | 9 2020/2021: 523000
0984981 | [N] C- SPS Cap Green Rockhampton Rd (possible INF Agreement) | Sewer | 350000 | 2020 | L/CW | 506847.7408 | 9 2020/2021: 350000
0984986 | [N] C-SPS Kinka Beach (Big Whale) | Sewer | 323000 | 2020 | L/CW | 467748.0579 | 9 2020/2021: 323000
0984957 | [N] M - SPS Carmody Bridge PS#4 | Sewer | 0 | 2020 | L/CW | 0 | 9 2020/2021: 0
0959069 | [N] C - S Main Zilzie West Trunk - design and construct | Sewer | 131000 | 2020 | L/CW | 189705.8687 | 9 2020/2021: 131000
0959072 | [N] C - S YSTP Augmentation Design & Construction | Sewer | 8000000 | 2020 | L | 11585091.2181 | 9 2020/2021: 8000000
0959073 | [N] C - SPS Zilzie West - Design & Construct | Sewer | 240000 | 2020 | L/CW | 347552.7365 | 9 2020/2021: 240000
0984961 | [N] C - SPS Shaw Ave | Sewer | 830000 | 2020 | L/CW | 1201953.2139 | 9 2020/2021: 830000
0984962 | [N] R - SPS Armstrong St (Gce) PS#1 | Sewer | 648000 | 2020 | L/CW | 938392.3887 | 9 2020/2021: 648000
0984963 | [N] R - SPS Breakspeare St (Gce) PS#6 | Sewer | 456000 | 2020 | L/CW | 660350.1994 | 9 2020/2021: 456000
0984975 | [N] R- S Main (Gravity) 225mm Belmont Rd | Sewer | 36000 | 2020 | L/CW | 52132.9105 | 9 2020/2021: 36000
0984976 | [N] C-S-Main (Gravity) 300mm James & Normanby Sts | Sewer | 189000 | 2020 | L/CW | 273697.78 | 9 2020/2021: 189000
0984977 | [N] C-S-Main (Gravity) 225mm Smith St | Sewer | 66000 | 2020 | L/CW | 95577.0025 | 9 2020/2021: 66000
0984978 | [N] C-S-Main (Gravity) 300mm Farnborough Rd & Smith St | Sewer | 210000 | 2020 | L/CW | 304108.6445 | 9 2020/2021: 210000
0984982 | [N] M - STP | Sewer | 0 | 2020 | L | 0 | 9 2020/2021: 0
0984983 | [N] C-S-Main (Rising) 200mm Hartley St Great Barrier Reef Resort | Sewer | 838000 | 2020 | L/CW | 1213538.3051 | 9 2020/2021: 838000
0984984 | [N] C-S-Main (Rising) 375mm Emu Park West PS#1 to STP | Sewer | 470000 | 2020 | L/CW | 680624.1091 | 9 2020/2021: 470000
0984985 | [N] R - S Main (Rising) 200mm Breakspeare St to STP | Sewer | 1100000 | 2020 | L/CW | 1592950.0425 | 9 2020/2021: 1100000
0984987 | [N] R - SPS Fisher St (Gce) PS#4 | Sewer | 432000 | 2020 | L/CW | 625594.9258 | 9 2020/2021: 432000
| R-STP Rton North | Sewer | 29282000 | 2021 | L | 44185311.9964 | 10 2021/2022: 29282000
| R-STP Rton South | Sewer | 21000000 | 2021 | L | 31688120.7542 | 10 2021/2022: 21000000
| R - SPS Edenbrook East | Sewer | 323000 | 2025 | L/CW | 574580.1096 | 14 2025/2026: 323000
| R - S Main (Gravity) 225mm Limestone Ck | Sewer | 158000 | 2025 | L/CW | 281063.9545 | 14 2025/2026: 158000
| R - S Main (Gravity) 225mm Ramsay Glen | Sewer | 63000 | 2025 | L/CW | 112069.8047 | 14 2025/2026: 63000
| R - S Main (Gravity) 225mm Stocklands | Sewer | 297000 | 2025 | L/CW | 528329.0791 | 14 2025/2026: 297000
| R - S Main (Rising) 200mm Edenbrook East | Sewer | 863000 | 2025 | L/CW | 1535178.4352 | 14 2025/2026: 863000
| R - SPS Hadgraft St PS#9 | Sewer | 378000 | 2025 | L/CW | 672418.8279 | 14 2025/2026: 378000
| R - S Main (Rising) 375mm from PS#9 SMH6994 | Sewer | 11000 | 2025 | L/CW | 19567.7437 | 14 2025/2026: 11000
| R - SPS Gavial Rd (Gce) PS#5 | Sewer | 391000 | 2025 | L/CW | 695544.3432 | 14 2025/2026: 391000
| R - SPS Bodero St PS#42 | Sewer | 516000 | 2025 | L/CW | 917905.0667 | 14 2025/2026: 516000
| C - S Main (Rising) 100mm Kemp Beach South | Sewer | 15000 | 2030 | L/CW | 32777.658 | 19 2030/2031: 15000
| R - S Main (Gravity) 375mm Glenmore Rd | Sewer | 1660000 | 2030 | L/CW | 3627394.1507 | 19 2030/2031: 1660000
| Total Proposed Cap X |  | 129274777 |  |  | 126339610.5358 | 8019732 | 8197984 | 15062868 | 12110193 | 11667000 | 800000 | 0 | 0 | 0 | 18460000 | 50282000 | 0 | 0 | 0 | 3000000 | 0 | 0 | 0 | 0 | 1675000 | 0
[7 empty] | 14907802 | 10813927 | 23246821 | 17496896 | 15866845 | 5950970 | 6381336 | 7198721 | 0 | 18762000 | 50396373 | 0 | 0 | 416625 | 3027517 | 10800 | 3606 | 0 | 0 | 1712123 | 10867
Projects submitted but not approved in 2012-13 as at 08-05-12
581005 | [N] C - Sewer Main (Gravity) Hidden Valley | 54957 |  |  |  |  | 2 2013/2014: 51557644
640283 | [N] R-STP Rton South (Pipeline from West Rton catchment) | 549569 |  |  |  |  | 2 2013/2014: balances to submitted
959061 | [N] S NRSTP Effluent Reuse Scheme | 219828
959062 | [N] C - S Main Kinka Stage 3 Design | 53121
959084 | [N] R - Misc CCTV Camera Unit | 28760
984902 | [N] C-S-Main Hidden Valley Sewerage (Gravity Trunk, SPS & Rising Main) - design | 76940
987648 | [U] R Glenmore Water Treatment plant amenities block | 43966
987934 | [N] R STP Microwave link to NRSTP and SRSTP | 19172
987935 | [N] R Tools of trade vehicle Treatment and Supply | 33553
Projects submitted but not approved in 2013-14 as at 08-05-12
640283 | [N] R-STP Rton South (Pipeline from West Rton catchment) | 1099138
Projects submitted but not approved in 2014-15 as at 08-05-12
640283 | [N] R-STP Rton South (Pipeline from West Rton catchment) | 1099138
984907 | [N] C-SPS Farnborough Road PS#2 | 912284
984919 | [N] C-S-Main (Rising) 200mm Farnborough Road Trunk | 531983
Note on B9: Karyn Beck: Tsf to c.0959079
Note on B26: Karyn Beck: Does not include SPS upgrades